## Sheet1
ID | Story | Estimation (hours) | Priority(1-3) | Sprint When Finished | Assignee | Resources
1 | Website Design
1.1 | Create initial NULL site via GitHub | 1 | 1 | 1 | Elizabeth
1.2 | Project Overview | 1 | 2 | 1 | Elizabeth
1.3 | Technical Features | 1 | 2 | 1 | Gage
1.4 | Design & Subpages | 1 | 2 | 1 | Andy
1.5 | Bio Page (Photo, Contact, Info,etc) | 1 | 2 | 1 | Charity
1.6 | Subpage of Project Deliverables |  | 1 | 3
1.6.1 | Add all Presentations to the site |  | 2 | 3
1.6.2 | Add all source code to website |  | 2 | 3
1.6.3 | Generate .apk file and insert link on site |  | 2 | 3
1.7 | Video |  | 2 | 3 | Charity
2 | Requirements & Analysis
2.1 | ER Diagram of Database | 1 | 2 | 1 | Gage
2.2 | Determine how the back-end database will interface with the user interface | 3 | 1 | 1 | Charity, Andy, Elizabeth
3 | Design & Implementation
3.1 | Implementation for backend of basketball fantasy sports first | 1 | 1 | 1 | Andy / Gage
3.1.1 | create Database | 1 | 1 | 1 | Gage
3.1.1.1 | Set up AWS and connect to python | 1 | 2 | 1 | Gage
3.1.1.2 | update NBA stats | 1 | 2 | 1 | Gage
3.1.1.3 | update NFL stats | 2 | 2 | 2 | Gage
3.1.2 | create linear regression model | 1 | 1 | 1 | Gage
3.1.2.1 | run regression and adjust it to be more accurate | 2 | 2 | 2
3.1.2.2 | adjust the r^2 and p values to get more accurate | 2 | 2 | 2
3.1.3 | create the optimizer | 1 | 2 | 1 | Gage
3.1.3.1 | specify it to each sport | 2 | 1 | 2 | Gage
3.1.4 | connect the back end to the front | 1 | 3 | 1 | Andy
3.1.4.1 | Set up web server in Python using Flask | 2 | 1 | 1 | Andy
3.1.4.2 | Set up get requesting to communicate with the web server | 2 | 1 | 1 | Andy
3.1.4.3 | Moved app development to EC2 Instance running apache | 4 | 3 | 2 | Andy
3.1.5 | Grab Draftkings slates in real time | 2 | 2 | 2 | Andy
3.1.5.1 | do this for every sport | 2 | 2 | 2 | Andy
3.1.5.2 | error message when out of season | 2 | 2 | 2 | Andy
3.1.6 | NFL optomization | 2 | 3 | 2 | Gage
3.1.6.1 | get optimizer made for fanduel | 3 | 3 | 2 | Gage
3.1.6.2 | get optimizer made for draftkings | 3 | 3 | 2 | Gage
3.1.6.3 | create functions to call optomizer and connect to the front end | 1 | 3 | 2 | Gage/Andy
3.1.7 | Change all requests to one main file | 1 | 1 | 2 | Gage/Andy
3.1.8 | Get Fanduel slates | 4 | 2 | 3 | Gage
3.1.9 | get projections from an API (ESPN) | 4 | 2 | 3 | Gage
3.1.10 | update fanduel costs | 4 | 3 | 3 | Gage
3.1.11 | update fanduel projections using web scraping | 3 | 3 | 3 | Gage
3.1.12 | update draftkings projections using web scrapping | 3 | 3 | 3 | Gage
3.1.13 | reformat to pair with front end requests | 1 | 2 | 3 | Gage
3.1.14 | Allow for multiple lineups for each sport | 2 | 2 | 3 | Gage
3.2 | Implementation for simple user interface to check that front end and back end can connect | 3 | 1 | 1 | Elizabeth / Charity
3.2.1 | User log in | 3 | 2 | 2 | Elizabeth / Charity
3.2.2 | If no account, have user sign up for an account -- name, email, username, password | 3 | 2 | 2 | Elizabeth / Charity
3.2.2.1 | Choose DraftKings / FanDuel & Select Sport | 1 | 2 | 1 | Charity
3.2.3 | Home page -- list populated sports' lineups & option to Edit generated lineup | 3 | 1 | 3 | Elizabeth
3.2.3.2 | Save option to store lineups to user's account | 5 | 1 | 3 | Charity
3.2.3.3 | List of players for that day (name of each player, remaining salary, etc.) so users can choose & Drop bar | 3.5 | 1 | 1 | Elizabeth
3.2.5.1 | Show detailed player description (photo/name of each player, position, team, salary, ranking, etc.) | 5 | 2 | 2 | Elizabeth
3.2.5.3 | Search bar for player names / positions | 4 | 1 | 2 | Charithy / Elizabeth | 48723.jpg
3.2.5.5 | Generate optimized lineup button &Display txt box | 1 | 2 | 1 | Elizabeth
3.2.6 | Conncect with the backend | 12 | 3 | 1 | Charity, Andy, Elizabeth
3.2.6.1 | Communication(send and receive requests) between UI and backend to get lineups | 3 | 3 | 1 | Charity, Andy, Elizabeth
3.2.6.2 | Parse incoming lineups (JSON to Java) | 3 | 2 | 1 | Charity
3.2.5.3 | Communication (send and receive requests) between UI and backend to get slates every day | 3 | 1 | 2 | Charity,Andy,Elizabeth
3.2.5.4 | Parse incoming slates (JSON to Java) | 3 | 1 | 2 | Charity,Andy,Elizabeth
3.3 | Display multiple lineups on the home page and display lineups page | 6 | 1 | 3 | Charity,Andy,Elizabeth
3.4 | Overall GUI cleanup | 10 | 1 | 3 | Charity,Andy,Elizabeth
4 | Testing & Demos
4.1 | Request tablet for emulator if no team members have an android device | ----- | ----- | ----- | N/A
4.2 | Create "test.py" to test java --> python compatibility. | 2 | 1 | 1 | Elizabeth
4.3 | Create test file to implement HTTP Connection | 0.5 | 1 | 1 | Charity
4.4 | 10 Test Cases for Sprint 2 | 6 | 1 | 2 | Charity, Andy, Elizabeth, Gage
4.4.1 | 3 test cases for password | 1.5 | 1 | 2 | Charity
4.4.2 | 2 test cases to check url | 1.5 | 1 | 2 | Andy
4.4.3 | 4 test cases for visibility | 1.5 | 1 | 2 | Elizabeth
4.4.4 | 3 test cases for backend | 1.5 | 1 | 2 | Gage
4.5 | 5 Test Cases for Sprint 3
4.5.1 | 2 test cases for spinner visibility | 1 | 1 | 3 | Elizabeth
4.5.2 | 1 test case for start of saved lineups class | 3 | 1 | 3 | Elizabeth
4.5.3 | 2 test cases for the backend |  |  |  | Gage